## Copy of Open Tasks
Type | Id | Status | Planned For | Summary | Owned By | Severity | Modified Date | Description | Filed Against | Priority | Created By
Task | 1208154 | New | Product Backlog | PIT 508 Compliance Validation Statement | Lee, Dana M. (GCIO) | 4 - Low | 2020-01-24 15:57 | Program Integrity Tool 508 Compliance Validation Statement | Documents | Unassigned | Lee, Dana M. (GCIO)
Task | 1208103 | New | Product Backlog | PIT AFMP | Lee, Dana M. (GCIO) | 4 - Low | 2020-01-24 15:39 | Program Integrity Tool AFMP | Documents | Unassigned | Lee, Dana M. (GCIO)
Task | 1207133 | In Progress | CC-PIT Backlog | Readiness Release Review - PIT V4.2.4 - Risk Log - Program Integrity Tool Enhancements GA RRR | Lee, Dana M. (GCIO) | 4 - Low | 2020-01-23 16:32 | RM.01.08.01 Release - Risks 01. All (100%) known project/product risks are logged as data in an OIT approved Change and Configuration Management (CCM) tool. 02. The Risk Log is applicable to the Product. 03. The Risk Log is current (minimally has been updated in the last 30 days). 04. All (100%) known risk log entries have a unique ID specified. 05. All (100%) known risk log entries have a risk name specified. 06. All (100%) known risk log entries have a description specified. 07. All (100%) known risk log entries have a probability specified. 08. All (100%) known risk log entries have an impact specified. 09. All 100%) known risk log entries have status specified. 10. All (100%) high exposure (probability/impact in Red zone on heat map) risks are (a) in either the Monitoring or Resolved Status; if in Monitoring Status, the risk has both a (a) Risk Response and (b) Risk Response Strategy specified. | Development | Unassigned | Haywood, Monique Y. (GCIO)
Task | 1005953 | In Progress | CCPIT_DB_Enhance_Rel_3_Patient_Data_Clean_Up | Uploading the AFMP | Unassigned | 4 - Low | 2019-06-06 13:25 | AFMP | Project Management | 3 - Normal Queue | Clark, Darnell A. (GCIO)
Task | 984851 | New | Database Cleanup | Requirement Specification Document (RSD) | Unassigned | 3 - Medium | 2019-04-23 10:55 | PIT-RSD | VHA_CBO_PC_PIT_Test_Cat_1 | Unassigned | Clark, Darnell A. (GCIO)
Task | 984734 | In Progress | Database Cleanup | Requirements Specification Document (RSD) | Unassigned | 4 - Low | 2019-06-06 13:26 | RSD | Project Management | Unassigned | Clark, Darnell A. (GCIO)
Task | 984411 | New | CC-PIT Backlog | Approval Signatures | Unassigned | 2 - High | 2019-09-12 16:29 | Release 1: Archiving: Approval Signatures were received. Uploading Approval Signatures. | Project Management | 2 - Give High Attention | Rachaputi, Sowmya P.
Task | 976557 | In Progress | CC-PIT Backlog | Complete the Quality Objectives Section of Test Plan: PIT Database Improvements Test Plan | Rachaputi, Sowmya P. | 2 - High | 2020-01-22 16:07 | Complete the Quality Objectives Section of Test Plan: PIT Database Improvements Test Plan | Testing | Unassigned | Rachaputi, Sowmya P.
Task | 963777 | New | CC-PIT Backlog | PIT Master Schedule | Unassigned | 4 - Low | 2019-09-27 16:27 | Program Integrity Tool Master Schedule | Project Management | Unassigned | Clark, Darnell A. (GCIO)
Task | 481639 | New | Build 2: Integration of the Extract into PIT (archived) | Risks - For Critical Decision 2 | Rachaputi, Sowmya P. | 4 - Low | 2017-03-16 09:31 | This should be fulfilled by managing Risks via the CCM tool, and the verification will be done by Risk Log report in Rational and looking at the status and the exposure. In lieu of using Rational a team can use the template archive for a Risk Log and baseline in the CCM PM folder. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 481350 | In Progress | Build 2: Integration of the Extract into PIT (archived) | PC-PIE Deployment, Installation, Back-Out, and Rollback Guide - For Critical Decision 2 | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | Recommend using the VIP template which has combined the various content sections together into one document (see VIP site). However as long as all the data specified in the .xls are present any number of documents can be submitted to cover this requirement. All documents being submitted to cover this content should be baselined in the Env_Depl_Imp folder in the Documentation baseline for each product being impacted by the release. All elements should be signed by the receiving organization. Content this release requirement must cover: Deployment Install Back-out Roll-back | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 481329 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Version Description Document - For Critical Decision 2 | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | Must use the VIP template for the initial product baseline, and then this baseline doc can be updated for every subsequent build leaving development. The VDD should be baselined in the CM CM folder of the Documentation baseline. VistA components (patches) also need a VistA patch description). Other CM documentation like the CM Procedures document should also exist in the CM folder, but will not be verified by the Release Agents. The CM Procedures may be reviewed as part of a CM audit. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 480877 | In Progress | Build 2: Integration of the Extract into PIT (archived) | From HAC Team - Traceability (requirements to test cases)/Test Execution/Test Results/Defect Log | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | Traceability, Test Execution, Test Results and Defect Logs should be data in Rational verified by examining in RM/CCM/QM that the release Epics and User Stories are covered in a Sprint Plan and there are subsequent test results including acceptance criteria. Defect Log will be verified by examining in Rational CCM by querying the Defect records related the release. If not doing testing using Rational yet, use the OIT templates: Test Evaluation, and Requirement Traceability Matrix, for guidance and place documents in the CCM Test folder and Requirements folder (respectively) of the Documentation baseline. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 472224 | In Progress | CC-PIT Backlog | Task 3: VIP Release Review - Requirements (Epics/User Stories) - PC-PIE 4.2.4 HAC Release | Chu, Yong Z. | 4 - Low | 2020-01-22 16:07 | Task 3: VIP Release Review - Requirements (Epics/User Stories) - PC-PIE 4.2.4 HAC Release | VHA_CBO_PC_PIT_Test_Cat_1 | Unassigned | Chu, Yong Z.
Task | 467008 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Traceability (requirements to test cases)/Test Execution/Test Results/Defect Log | Rachaputi, Sowmya P. | 4 - Low | 2017-02-20 11:05 | Traceability, Test Execution, Test Results and Defect Logs should be data in Rational verified by examining in RM/CCM/QM that the release Epics and User Stories are covered in a Sprint Plan and there are subsequent test results including acceptance criteria. Defect Log will be verified by examining in Rational CCM by querying the Defect records related the release. If not doing testing using Rational yet, use the OIT templates: Test Evaluation, and Requirement Traceability Matrix, for guidance and place documents in the CCM Test folder and Requirements folder (respectively) of the Documentation baseline. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 465386 | In Progress | Build 2: Integration of the Extract into PIT (archived) | PC-PIE Deployment, Installation, Back-Out, and Rollback Guide | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | Recommend using the VIP template which has combined the various content sections together into one document (see VIP site). However as long as all the data specified in the .xls are present any number of documents can be submitted to cover this requirement. All documents being submitted to cover this content should be baselined in the Env_Depl_Imp folder in the Documentation baseline for each product being impacted by the release. All elements should be signed by the receiving organization. Content this release requirement must cover: Deployment Install Back-out Roll-back | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 465040 | In Progress | Build 2: Integration of the Extract into PIT (archived) | PC-PIE_PIT - Repository User Guide | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:48 | Your product may not have any User Guides; but if a User Guide exists please include in your Documentation baseline, and keep in the Env_Depl_Imp folder. There is a VIP User Guide template. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 464003 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Version Description Document | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | Must use the VIP template for the initial product baseline, and then this baseline doc can be updated for every subsequent build leaving development. The VDD should be baselined in the CM CM folder of the Documentation baseline. VistA components (patches) also need a VistA patch description). Other CM documentation like the CM Procedures document should also exist in the CM folder, but will not be verified by the Release Agents. The CM Procedures may be reviewed as part of a CM audit. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 461753 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Approved System Design Document | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | If requirements are not in the RM module, use the archived OIT templates for BRD, RSD, SDD as a reference, and baseline the documents in the in the CCM Requirements folder. Regardless of whether in docs or RM the requirements should cover, as applicable to the release: Business requirements, Functional, Non-Functional (Architectural, Performance, Capacity, etc.), Technical. The Release Agent will be verifying that they exist and are approved, either as a document or within the RM tool as data. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 461747 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Approved Business Requirements Document | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | If requirements are not in the RM module, use the archived OIT templates for BRD, RSD, SDD as a reference, and baseline the documents in the in the CCM Requirements folder. Regardless of whether in docs or RM the requirements should cover, as applicable to the release: Business requirements, Functional, Non-Functional (Architectural, Performance, Capacity, etc.), Technical. The Release Agent will be verifying that they exist and are approved, either as a document or within the RM tool as data. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 461722 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Approved Requirements Specification Document | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | If requirements are not in the RM module, use the archived OIT templates for BRD, RSD, SDD as a reference, and baseline the documents in the in the CCM Requirements folder. Regardless of whether in docs or RM the requirements should cover, as applicable to the release: Business requirements, Functional, Non-Functional (Architectural, Performance, Capacity, etc.), Technical. The Release Agent will be verifying that they exist and are approved, either as a document or within the RM tool as data. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 423767 | In Progress | Build 2: Integration of the Extract into PIT (archived) | 508 Compliance | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | The 508 Office's Final Validation Statement, signed by the 508 Office, must be baselined in the Test folder of the Documentation stream, or this item will fail. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 423766 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Authority to Operate (ATO) | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | This needs to be the ATO approval memo stored as an artifact baselined in the PM folder of the Documents baseline. Achieving an ATO assumes all docs needed for an approved ATO are complete and on file in Riskvision. Release Agents are not responsible for verifying any of the underlying ATO requirements. This requirement will fail if an ATO is not provided or if a temporary ATO is expired. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 380146 | In Progress | Build 2: Integration of the Extract into PIT (archived) | Risks | Rachaputi, Sowmya P. | 4 - Low | 2017-02-17 10:52 | This should be fulfilled by managing Risks via the CCM tool, and the verification will be done by Risk Log report in Rational and looking at the status and the exposure. In lieu of using Rational a team can use the template archive for a Risk Log and baseline in the CCM PM folder. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 379767 | In Progress | Build 2: Integration of the Extract into PIT (archived) | SLA's & OLA's | Rachaputi, Sowmya P. | 4 - Low | 2020-01-22 16:07 | This should be the SLA-OLA completed during CD1, using the VIP template. Note: SLA is the product owners service level agreement with OIT and the customer, and the OLA would be any external agreements between the service teams in support of the SLA. These should baselined in the Documents PM folder. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.
Task | 375275 | New | Build 2: Integration of the Extract into PIT (archived) | Acquisition Management and Financial Planning | Rachaputi, Sowmya P. | 4 - Low | 2017-03-08 15:41 | This should be the Acquisition Financial Management Plan using the VIP template, AFMP, done for CD1. It needs to baselined in Rational in the PM folder by CD1 to be verified as baselined in Rational by the RA in the first sprint after CD1. If it needs to be updated subsequent to CD1, then proper source control needs to be done to update and be re-verified by the RA. | VIP Compliance Category | Unassigned | Rachaputi, Sowmya P.