## Sheet1
[PROJECT NAME] Rational Close-out Activities - End of Project
Use this template to close out Rational tools once a project team is nearing or is at conclusion of their woek efforts in the repository
Tool | Topic | Recommended Action Items | Additional Action Items | Date Completed | Comments
Rational DOORS Next Generation (RDNG)
Requirements Artifacts
|  | Update them to ensure their status has been corrected to reflect satisfaction to schedule. |  |  | Status of artifacts are set to Development Complete
Reference any externally built requirements artifacts in appropriate entries to enhance the descriptions of the requirements communicated.
Ensure all artifacts are linked to RTC Work Items to reflect specific work items accomplished.
|  | Ensure all artifacts are in appropriate folders in RDNG. |  |  | Artifacts should not be stored in the root.
|  | Take final baseline of delivered requirements. |  |  | Requires Baseline Administrator role in project area.
Rational Team Concert (RTC)
Work Items
Ensure that all data records in RTC are linked to related data records in the RQM and RDNG associated repositories.
|  | Ensure all data records in RTC are linked to other necessary data records to show relationship between changes, risks, issue, etc. for the full documentation of what work was performed to resolve reports captured of the other project information. |  |  | Any open Risks/Issues should be moved to the Backlog.
Update all work items (change orders, risk, issue, etc.) to ensure all completed work items are in the last status, usually Done.
Source control files
Make sure all source code, documents and other deliverables are checked back into RTC from other sources.
Make sure your final baseline shows proper content and delivered version.
|  | Update all files to ensure there are no lingering locks on files in source control. |  |  | Use Eclipse to search for Locks.
Work with your Configuration Manager to perform an audit of all content to meet CM best practices on trace history and final deliverables.
Categories
Ensure that any categories associated to the team to be archived are visible to all, accessible to all, and archived.
Be sure you do not archive all categories.
Timelines
Make sure that your backlogs correctly reflect items that were not delivered.
|  | Archive the timeline associated to the team unless it is the only timeline or is being used by another team area. |  |  | Timelines can be restored with a service request to RTT.
If it is the only timeline, archive the iterations that are completed, ensuring there is at least one backlog still active.
Streams
Add clear descriptions to all existing Streams including status of the component(s) in the stream.
Check to ensure Streams are owned by the correct Project or Team Area and that users have access as needed.
Add Components to Sustainment/Archived streams as needed.
Remove any Streams that are not needed.
Plans
Take final Snapshot of Plans.
Rational Quality Manager (RQM)
Test Artifacts
Ensure that any test execution information that has been managed outside the tool is at least checked into RTC as a record of its execution.
Ensure all test execution data records are linked to their related requirements artifacts in RDNG and their work items in RTC.
|  | Update all artifacts to ensure all completed test plans, test cases, test case execution records, etc. are in the status of Retired. |  |  | Verified with Rational Tools Team that items moved to Retired can be Reopened if needed.
|  | Create Snapshots of Test Plans |  |  | Test Plan Snapshot captures Test Plan, Test Cases and Test Scripts.
Workspace Security
Jazz Environment
|  | Make a list of all the team members who are no longer working in the individual team designations within the project area. Determine if team needs to have read only access or no access to the specifically defined team area. |  |  | Submit Service Request to RTT with user list to remove users as needed.
Determine if the parent product /project area itself should have role/access modified.
|  | Determine at which level, if any, to archive the team or project spaces. |  |  | Submit Service Request to RTT to archive team areas or project areas. All user access will be removed from those areas.
|  | Update Rational POCs for the product. |  |  | Submit a Service Request to the RTT to update Rational POCs as needed so that the responsible VA PM is listed for the repository.
Upload final User Inventory, Service Request Tracker and Project Close Task spreadsheet to source control.
Submit updated user and workspace area requests to the Rational Tools Team at rational@va.gov.